## Planning
November
21, November, 2023, Tuesday |  | Targets | Spending Time | Developer Comments
| 1 | Do backlink audit | 2 Hours | Pending
| 2 | Build Backlinks atleast 20 | 3 Hours | Pending
22,November,2023, Wednesday |  | Targets | Spending Time | Developer Comments
| 1 | Do backlink audit | 2 Hours | Pending
| 2 | Build Backlinks atleast 20 | 3 Hours | Pending
| 3 | Make loading screens for vehiclemasti | 1 Hour | Done
| 4 | Make loading screens for patel'sBlog & Sync up with Vehicle Masti Blog | 2 Hour | Done
| 5 | Desing & Publish OG Images for all pages and websites | 2 Hour | Done
| 6 | Create strong, outbound links & inbound links inside blog post and publish the changes for both websites | 2 Hour | Pending
| 7 | Build a gallery and lighthouse feature for VehicleMasti | 1 Hour | This cannot be done, I tried but it was reflecting the perfromance of the whole webpage.
23,November,2023, Thursday |  | Targets | Spending Time | Developer Comments
| 1 | Do backlink audit | 3 Hours | Pending
| 2 | Build Backlinks atleast 20 | 3 Hours | Pending
| 3 | Create strong, outbound links & inbound links inside blog post and publish the changes for both websites | 2 Hour | Pending
| 4 | Test & Verify the Both Websites and make it to sync with one another | 2 Hour | Pending

## Backlogs
| Backlogs | Developer Comments
1 | Build a gallery and lighthouse feature for VehicleMasti
2 | Make loading screen for both the websites
3 | Make Patel's Website upto date with VehicleMasti Blog
4 | Publish recent post on the bottom of the Blog Post

## Backlink_Audit
Backlinks
smira.org.uk | https://www.dofollowwebsite.com/published
http://www.spectrumcommunications.ie/nortel-bcm-50450-end-of-life/#comment-236383
https://demcra.com/r/business/1146476_Tata_Safari_Facelift_2023_A_Closer_Look_Into_Modern_SUV
https://www.truelovetattoos.it/2016/12/26/add-videos-to-blog-posts/#comment-69235